## Developments
Task ID | Description | Screenshot Id | Delivery Date | In Progress | Closed
DEV0001 | Add autowiring for hibernate connection bean. |  | 2020-01-26
DEV0002 | Add valid testcases for all Services and test them. |  | 2020-02-24
DEV0003 | Add Invalid testcases for all Services and test them. |  | 2020-02-24
DEV0004 | Use Enum instead String in all applicable fields. |  | 2020-02-25
DEV0005 | Hibernate field Annotations.(length, lettercase, pattern e.t.c) and Test It |  | 2020-02-26
DEV0006 | One To Many Pattern |  | 2020-02-26 |  |  | To be focused after developing order views
DEV0007 |  |  | 2020-02-27
DEV0008 | Create Email Bean |  | 2020-02-28 |  |  | Moving to Change Request #CHG0002
DEV0009 | Use Criteria instead of QueryText |  | 2020-02-28 |  |  | To be focused after developing views
DEV0010 | Add Rating Model, dao and service, service impl |  | 2020-02-28
DEV0011 | InstaMojo Integration |  | 2020-02-29 |  |  | To be focused after developing order views
DEV0012 | PayTM Integration |  | 2020-03-01 |  |  | To be focused after developing order views
DEV0013 | Expose Rest API
DEV0014 | Do url mapping
DEV0015 | Spring Security
DEV0016 | Payment Job Process - (Timestamp and Timestamp + 15 minutes.)
DEV0017 | Create Email Bean
DEV0018 | Add Link Model, dao and service, service impl |  |  |  |  | To be focused after developing order views
DEV0019
DEV0020
DEV0021
DEV0022
DEV0023
DEV0024
DEV0025
DEV0026

## Bugs
Task ID | Description | Screenshot Id | Delivery Date | In Progress | Closed | Developer Note
BUG0001 | Multiple Test Case fails for update Service - 'Transaction Already Active'. |  | 2020-02-24 |  |  | followed Spring.io Documentation - Session.closed in finally, transaction rolled back in catch.
BUG0002 | Middleware pom.wml packing warning. Fix it. |  | NA
BUG0003
BUG0004
BUG0005
BUG0006
BUG0007
BUG0008
BUG0009
BUG0010
BUG0011
BUG0012
BUG0013
BUG0014
BUG0015
BUG0016
BUG0017
BUG0018
BUG0019
BUG0020
BUG0021
BUG0022
BUG0023
BUG0024
BUG0025
BUG0026
BUG0027

## Enhancements
Task ID | Description | Screenshot Id | Delivery Date | In Progress | Closed
ENC0001
ENC0002
ENC0003
ENC0004
ENC0005
ENC0006
ENC0007
ENC0008
ENC0009
ENC0010
ENC0011
ENC0012
ENC0013
ENC0014
ENC0015
ENC0016
ENC0017
ENC0018
ENC0019
ENC0020
ENC0021
ENC0022
ENC0023
ENC0024
ENC0025
ENC0026

## Change Request
Task ID | Description | Screenshot Id | Delivery Date | In Progress | Closed
CHG0001 | Primary Key Replace numeric with UUID |  | 2020-03-01
CHG0002 | Replace Apache Email with Spring Boot Mail Starter |  | 2020-03-02
CHG0003 | Create webapp for testing backend for now. |  | 2020-03-22
CHG0004 | Create Google forms for user feedback |  | NA
CHG0005
CHG0006
CHG0007
CHG0008
CHG0009
CHG0010
CHG0011
CHG0012
CHG0013
CHG0014
CHG0015
CHG0016
CHG0017
CHG0018
CHG0019
CHG0020
CHG0021
CHG0022
CHG0023
CHG0024
CHG0025
CHG0026

## Screenshots
Screenshot #1